## Delivery Features
EKART — Delivery Feature Coverage: HTML vs React
Detailed comparison of every delivery feature — what exists in Thymeleaf HTML and what has been migrated to React
# | Feature / Sub-Feature | Category | In HTML (Thymeleaf) | In React (Migrated) | HTML Page(s) | React Component / File | Notes / Gap
─── DELIVERY BOY AUTHENTICATION
1 | Delivery Boy Registration Form | Auth | ✅ Done | ❌ Missing | delivery-register.html | — | HTML-only: name, email, mobile, password, vehicle fields via POST /delivery/register
2 | Registration Email OTP Verification | Auth | ✅ Done | ❌ Missing | delivery-otp.html | — | 6-digit OTP page after registration. No React equivalent; DeliveryApp skips auth — handled by App.jsx JWT flow
3 | Delivery Login Page | Auth | ✅ Done | ❌ Missing | delivery-login.html | — | HTML-only. React uses shared AuthPage (JWT). HTML delivery login is a separate standalone form
4 | Pending Approval Waiting Screen | Auth | ✅ Done | ✅ Done | delivery-pending.html | DeliveryApp.jsx | Both show pending state. React shows it inline (guard) inside DeliveryApp when profile.approved=false
5 | Logout | Auth | ✅ Done | ✅ Done | delivery-home.html | DeliveryApp.jsx | HTML → /delivery/logout. React → JWT logout() + navigate /auth
─── DELIVERY BOY DASHBOARD
6 | Welcome Banner (Name + Code) | Dashboard | ✅ Done | ✅ Done | delivery-home.html | DeliveryApp.jsx | Both show delivery boy name, code, assigned pin codes
7 | Assigned Warehouse Card | Dashboard | ✅ Done | ✅ Done | delivery-home.html | DeliveryApp.jsx | Both show warehouse name, city, state, code; 'No warehouse assigned' fallback
8 | Summary Stats (Pickup / OFD / Done) | Dashboard | ✅ Done | ✅ Done | delivery-home.html | DeliveryApp.jsx | 3-stat counters: To Pick Up, Out for Delivery, Delivered
9 | Online / Offline Availability Toggle | Dashboard | ❌ Missing | ✅ Done | — | DeliveryApp.jsx | React-only feature! HTML page has no availability toggle. Button toggles via POST /delivery/availability/toggle
10 | Alert / Flash Message Stack | Dashboard | ✅ Done | ✅ Done | delivery-home.html | DeliveryApp.jsx | Both support dismissable alerts. React uses toast instead of server flash
─── ORDER PICKUP WORKFLOW
11 | To-Pick-Up Orders List | Pickup | ✅ Done | ✅ Done | delivery-home.html | DeliveryApp.jsx (ToPickUp panel) | Lists orders assigned to this delivery boy that are PACKED at warehouse
12 | Order Detail: ID, Customer, Mobile | Pickup | ✅ Done | ✅ Done | delivery-home.html | DeliveryApp.jsx | Shows order ID, customer name, mobile number
13 | Order Detail: Delivery PIN Code | Pickup | ✅ Done | ✅ Done | delivery-home.html | DeliveryApp.jsx | Shows destination PIN code on order card
14 | Order Detail: Items List | Pickup | ✅ Done | ✅ Done | delivery-home.html | DeliveryApp.jsx | Shows item name × quantity for each item in order
15 | Order Detail: Total Amount | Pickup | ✅ Done | ✅ Done | delivery-home.html | DeliveryApp.jsx | Shows formatted ₹ amount of order
16 | 'Picked Up' Button (Mark Pickup) | Pickup | ✅ Done | ✅ Done | delivery-home.html (confirmPickup()) | DeliveryApp.jsx (markPickedUp()) | POST /delivery/order/{id}/pickup. Moves order to Out for Delivery list
─── OUT FOR DELIVERY WORKFLOW
17 | Out-for-Delivery Orders List | OFD | ✅ Done | ✅ Done | delivery-home.html | DeliveryApp.jsx (OutNow panel) | Lists orders currently in OUT_FOR_DELIVERY status
18 | PIN Code Highlight on Active Orders | OFD | ✅ Done | ✅ Done | delivery-home.html (yellow highlight) | DeliveryApp.jsx (.dk-order-pin.highlight) | PIN shown in accent color for active delivery orders
19 | OTP Input Field (6-digit) | OFD | ✅ Done | ✅ Done | delivery-home.html (otp-input) | DeliveryApp.jsx (otpMap state) | Numeric input; HTML uses per-order id='otp-{id}'; React uses otpMap[orderId]
20 | 'Deliver' Button + OTP Validation | OFD | ✅ Done | ✅ Done | delivery-home.html (confirmDeliver()) | DeliveryApp.jsx (confirmDelivery()) | POST /delivery/order/{id}/deliver with OTP FormData; validates 6-digit before sending
─── DELIVERED ORDERS HISTORY
21 | Delivered Orders List (Today) | History | ✅ Done | ✅ Done | delivery-home.html | DeliveryApp.jsx (Delivered panel) | Both show completed deliveries with dimmed/opacity styling
22 | Delivered Order Detail | History | ✅ Done | ✅ Done | delivery-home.html | DeliveryApp.jsx | Shows order ID, customer name, items, amount for delivered orders
─── WAREHOUSE TRANSFER REQUEST
23 | Request Warehouse Transfer Button | Warehouse | ✅ Done | ✅ Done | delivery-home.html (openChangeModal()) | DeliveryApp.jsx (openTransferModal()) | Opens modal if no pending transfer request
24 | Transfer Modal: Select Warehouse | Warehouse | ✅ Done | ✅ Done | delivery-home.html (changeModal) | DeliveryApp.jsx (transferModal) | Dropdown of all warehouses, excludes current one
25 | Transfer Modal: Reason Field | Warehouse | ✅ Done | ✅ Done | delivery-home.html | DeliveryApp.jsx | Optional textarea for transfer reason
26 | Submit Transfer Request | Warehouse | ✅ Done | ✅ Done | delivery-home.html | DeliveryApp.jsx (submitTransfer()) | POST /delivery/warehouse-change/request
27 | Pending Transfer Badge (status) | Warehouse | ✅ Done | ✅ Done | delivery-home.html (pending badge) | DeliveryApp.jsx (pendingTransfer) | Shows 'Transfer to X — Pending' badge when request exists; hides transfer button
─── ADMIN — DELIVERY BOY MANAGEMENT
28 | Admin Delivery Management Page | Admin | ✅ Done | ✅ Done | admin-delivery-management.html | AdminApp.jsx (DeliveryAdmin component) | Full delivery management section for admin
29 | Pending Delivery Boy Approvals List | Admin | ✅ Done | ✅ Done | admin-delivery-management.html | AdminApp.jsx | Lists self-registered, OTP-verified delivery boys awaiting approval
30 | Assign Warehouse to Delivery Boy | Admin | ✅ Done | ✅ Done | admin-delivery-management.html | AdminApp.jsx (approvalWh state) | Dropdown to assign warehouse before approving
31 | Assign Pin Codes to Delivery Boy | Admin | ✅ Done | ✅ Done | admin-delivery-management.html | AdminApp.jsx (approvalPins state) | Text input for comma-separated pin codes this delivery boy covers
32 | Approve Delivery Boy | Admin | ✅ Done | ✅ Done | admin-delivery-management.html (approveDB()) | AdminApp.jsx (approveDelivery()) | POST /admin/delivery/boy/approve (HTML) ¦ /admin/delivery-boys/{id}/approve (React)
33 | Reject Delivery Boy | Admin | ✅ Done | ✅ Done | admin-delivery-management.html (rejectDB()) | AdminApp.jsx (rejectDelivery()) | Prompt for rejection reason; emails delivery boy
34 | Warehouse Transfer Requests Table | Admin | ✅ Done | ✅ Done | admin-delivery-management.html | AdminApp.jsx | Shows delivery boy, current warehouse → requested warehouse, reason, date
35 | Approve Warehouse Transfer | Admin | ✅ Done | ✅ Done | admin-delivery-management.html | AdminApp.jsx (approveTransfer()) | Optional note prompt, then POST approve
36 | Reject Warehouse Transfer | Admin | ✅ Done | ✅ Done | admin-delivery-management.html | AdminApp.jsx (rejectTransfer()) | Reason prompt, then POST reject
─── ADMIN — ORDER → DELIVERY BOY ASSIGNMENT
37 | Packed Orders — Assign Delivery Boy | Admin | ✅ Done | ✅ Done | admin-delivery-management.html | AdminApp.jsx | Table of PACKED orders; admin picks eligible delivery boy per order
38 | Eligible Delivery Boys Dropdown | Admin | ✅ Done | ✅ Done | admin-delivery-management.html | AdminApp.jsx (eligibleMap) | Fetches /admin/delivery/boys/for-order/{id}; filtered by PIN code; shows 🟢/🔴 availability
39 | Assign Delivery Boy Action | Admin | ✅ Done | ✅ Done | admin-delivery-management.html (assignDeliveryBoy()) | AdminApp.jsx (assignDeliveryBoy()) | POST /admin/delivery/assign with orderId + deliveryBoyId
40 | Shipped Orders View | Admin | ✅ Done | ✅ Done | admin-delivery-management.html | AdminApp.jsx (shippedOrders) | Table of SHIPPED orders with assigned delivery boy name
41 | Out for Delivery Orders View | Admin | ✅ Done | ✅ Done | admin-delivery-management.html | AdminApp.jsx (outOrders) | Table of OUT_FOR_DELIVERY orders with delivery boy name
─── ADMIN — WAREHOUSE MANAGEMENT
42 | Warehouse List / Management Page | Warehouse | ✅ Done | ✅ Done | admin-warehouse.html | AdminApp.jsx (WarehouseAdmin) | Manage warehouses: list, add new
43 | Add New Warehouse | Warehouse | ✅ Done | ✅ Done | admin-warehouse.html | AdminApp.jsx | POST /admin/delivery/warehouse — name, city, state, pin codes, code fields
44 | Link to Warehouse Management | Warehouse | ✅ Done | ✅ Done | admin-delivery-management.html | AdminApp.jsx | Button/link in delivery page to navigate to warehouse section
─── CUSTOMER — ORDER TRACKING
45 | Track Orders Page (All Active Orders) | Customer | ✅ Done | ✅ Done | track-orders.html | CustomerApp.jsx (TrackOrdersPage) | Lists active orders with status pipeline, progress indicators
46 | Order Status Pipeline (5 steps) | Customer | ✅ Done | ✅ Done | track-orders.html | CustomerApp.jsx | PROCESSING → PACKED → SHIPPED → OUT_FOR_DELIVERY → DELIVERED
47 | Progress Bar per Order | Customer | ❌ Missing | ✅ Done | — | CustomerApp.jsx (PROGRESS map) | React-only: animated gradient progress bar with % complete. HTML uses step dots only
48 | Single Order Deep-Track Page | Customer | ✅ Done | ✅ Done | track-single-order.html | CustomerApp.jsx (TrackSingleOrderPage) | Detailed view: pipeline, shipment info, items, estimated delivery
49 | Live Tracking History (Events from DB) | Customer | ❌ Missing | ✅ Done | — | CustomerApp.jsx | React-only: fetches /api/react/orders/{id}/track for real timestamped tracking events with location
50 | Estimated Delivery Date Display | Customer | ✅ Done | ✅ Done | track-single-order.html | CustomerApp.jsx | Both show estimated delivery date from server
51 | Current City / Location Display | Customer | ⚠️ Partial | ✅ Done | track-orders.html (city fallback) | CustomerApp.jsx (currentCity) | React fetches live currentCity from tracking API. HTML shows currentCity only if set on order
52 | CANCELLED / REFUNDED Status Banners | Customer | ✅ Done | ✅ Done | track-single-order.html, track-orders.html | CustomerApp.jsx | Both handle terminal states with special banners/styling
53 | Tracking History Event Log | Customer | ❌ Missing | ✅ Done | — | CustomerApp.jsx (history events) | React-only: timestamped event timeline (status, description, location, timestamp) from DB
─── CUSTOMER — ORDER MANAGEMENT
54 | Order History / My Orders Page | Customer | ✅ Done | ✅ Done | order-history.html (HTML) / track-orders.html | CustomerApp.jsx (OrdersPage) | Both show full order history with status badges
55 | Order Status Badges (color coded) | Customer | ✅ Done | ✅ Done | order-history.html | CustomerApp.jsx | Color-coded: PLACED, CONFIRMED, SHIPPED, OFD, DELIVERED, CANCELLED
56 | Cancel Order Button | Customer | ✅ Done | ✅ Done | order-history.html (view-orders.html) | CustomerApp.jsx (cancelOrder()) | Shown for PLACED/CONFIRMED/SHIPPED/OFD; hidden for DELIVERED/CANCELLED
57 | Reorder Button | Customer | ✅ Done | ✅ Done | track-orders.html (quickReorder()) | CustomerApp.jsx (reorderItems()) | Shown for DELIVERED orders; checks stock before reordering
58 | Reorder Stock Check Modal | Customer | ❌ Missing | ✅ Done | — | CustomerApp.jsx (ReorderStockModal) | React-only: shows which items are out of stock before confirming reorder
59 | Refund Report Button | Customer | ✅ Done | ✅ Done | track-orders.html, order-history.html | CustomerApp.jsx | Links to refund report for non-cancelled/refunded orders
60 | Delivery Charge Display | Customer | ✅ Done | ✅ Done | order-history.html | CustomerApp.jsx | Shows delivery charge if > 0
61 | Delivery Time / Speed Option | Customer | ✅ Done | ✅ Done | order-history.html | CustomerApp.jsx (PaymentPage) | STANDARD / EXPRESS delivery time selection at checkout
─── CUSTOMER — DELIVERY PIN & LOCATION
62 | Delivery PIN Entry (Sticky Bar) | Customer | ❌ Missing | ✅ Done | — | CustomerApp.jsx (PinBar component) | React-only: sticky PIN code bar at top; filters products by serviceability
63 | PIN-based Product Serviceability Check | Customer | ❌ Missing | ✅ Done | — | CustomerApp.jsx (isPinAllowed()) | React-only: checks product.deliveryPinCodes before allowing add-to-cart
64 | PIN Restriction Warning at Checkout | Customer | ❌ Missing | ✅ Done | — | CustomerApp.jsx (placeOrder()) | React-only: blocks order if items can't be delivered to selected address PIN
65 | Delivery Address PIN Extraction | Customer | ❌ Missing | ✅ Done | — | CustomerApp.jsx | React auto-extracts PIN from selected address.postalCode for validation
─── CUSTOMER — DELIVERY OTP
66 | Delivery OTP Email to Customer | OTP | ✅ Done | ✅ Done | delivery-otp-email.html (email template) | Backend (service layer) | Email sent when order marked OUT_FOR_DELIVERY with 6-digit OTP for delivery verification
67 | OTP Display in Order Page | OTP | ❌ Missing | ❌ Missing | — | — | OTP is emailed only; neither HTML nor React shows it on the order page
68 | OTP Verification (Delivery Boy side) | OTP | ✅ Done | ✅ Done | delivery-home.html | DeliveryApp.jsx | Delivery boy enters customer OTP to confirm delivery
─── DELIVERY EMAIL NOTIFICATIONS
69 | Order Shipped Email | Email | ✅ Done | ✅ Done | shipped-email.html | Backend (CartOrderApiController) | Sent when status → SHIPPED
70 | Out for Delivery Email | Email | ✅ Done | ✅ Done | delivery-otp-email.html | Backend | Sent when delivery boy picks up; includes OTP
71 | Order Delivered Email | Email | ✅ Done | ✅ Done | delivered-email.html | Backend | Sent when OTP-confirmed delivery
72 | Delivery Boy Approval Email | Email | ✅ Done | ✅ Done | (service layer) | Backend | Sent to delivery boy when admin approves/rejects their application
─── ADMIN — ORDER STATUS MANAGEMENT
73 | Admin View Orders (All Statuses) | Admin | ✅ Done | ✅ Done | view-orders.html | AdminApp.jsx (OrdersAdmin) | Admin sees all orders, can filter by status
74 | Order Status Dropdown (Admin Update) | Admin | ✅ Done | ✅ Done | view-orders.html | AdminApp.jsx | Admin can manually update any order status
75 | Status Filter Buttons | Admin | ✅ Done | ✅ Done | view-orders.html | AdminApp.jsx | Filter by PLACED, CONFIRMED, SHIPPED, OFD, DELIVERED, CANCELLED
76 | Status Count Summary | Admin | ✅ Done | ✅ Done | view-orders.html | AdminApp.jsx (statusCounts) | Bar/count of orders by trackingStatus

## Migration Summary
EKART Delivery — React Migration Summary & Gap Analysis
| Metric | Count
| Total Delivery Features Tracked | 76
| ✅ In HTML (Thymeleaf) | 64
| ✅ In React (Migrated/Implemented) | 65
| ❌ In HTML but NOT in React | 4
| ✅ In React but NOT in HTML (React-Only / New) | 10
| ⚠️ Partial in HTML, Full in React | 1
Migration Coverage %
❌ Missing in React — Features only in HTML (Need Migration)
| Feature | HTML Source | Recommended Action
| Delivery Boy Registration Form (HTML-only) | /delivery/register → delivery-register.html | Create a React registration page inside AuthPage or DeliveryApp
| Email OTP Verification for Delivery Boy | /delivery/otp/{id} → delivery-otp.html | Build React OTP verification step after delivery registration
| Delivery Boy Login Page (standalone HTML form) | /delivery/login → delivery-login.html | React AuthPage already has JWT login; ensure routing for delivery role
🚀 React-Only Features (New Capabilities — NOT in HTML)
| Feature | React Component | Description
| Online/Offline Availability Toggle | DeliveryApp.jsx | Delivery boy can toggle availability; admin sees 🟢/🔴
| Live Tracking API + Event History | CustomerApp.jsx (TrackSingleOrderPage) | Fetches /api/react/orders/{id}/track for real-time events with timestamp + location
| Progress Bar on Track Orders | CustomerApp.jsx (TrackOrdersPage) | Animated gradient progress bar showing % complete
| Reorder Stock Check Modal | CustomerApp.jsx | Pre-reorder modal shows which items are out of stock
| Delivery PIN Sticky Bar | CustomerApp.jsx (PinBar) | Sticky top bar for customer to enter/change delivery PIN
| PIN-based Product Serviceability Filter | CustomerApp.jsx (isPinAllowed) | Hides/warns about products not deliverable to PIN
| PIN Restriction Block at Checkout | CustomerApp.jsx (placeOrder()) | Prevents order placement if items can't reach selected address PIN
| Delivery Address PIN Auto-extraction | CustomerApp.jsx | Reads postalCode from address object for PIN validation
| Admin: Delivery Boy Count Badge on Tab | AdminApp.jsx | Badge shows pending approvals count on Delivery nav tab
| Admin: Order Status Filter by TrackStatus | AdminApp.jsx (OrdersAdmin) | Filter buttons for each tracking status with live counts